## Sheet1
HARDWARE DESIGN VERIFICATION CHECKLIST
TASKS / SUBTASKS | Before 2014/12/3 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-11 | 2014-12-12 | 2014-12-13 | 2014-12-14 | 2014-12-15 | 2014-12-16 | 2014-12-17 | 2014-12-18
Subunits compile and simulate clean
VCS compile for each subunit without unexpected warnings
module FF | done
module mux(two-to-one 17-bit) | done
module comparator | done
module register | done
module counter | done
module header_body_record | done
module header_body_logic | done
module buffer_storage |  | 2014-12-03: done
module chooser | done
module arbiter_logic | done
module arbiter |  | 2014-12-12: done
module direction_analyzer |  | 2014-12-11: done
module com_dir_logic | done
module valid_tester | done
module output_data_logic |  | 2014-12-11: done
module crossbar_switch |  | 2014-12-11: done
module input_buffer |  | 2014-12-03: done
module router |  | 2014-12-13: BUG; 2014-12-14: BUG; 2014-12-15: done
module network |  | 2014-12-17: done
DC compile (elaborate and check) for each subunit without unexpected warnings
module FF |  | 2014-12-03: done
module mux(two-to-one 17-bit) |  | 2014-12-03: done
module comparator |  | 2014-12-03: done
module register |  | 2014-12-03: done
module counter |  | 2014-12-03: done
module header_body_record |  | 2014-12-11: done
module header_body_logic |  | 2014-12-11: done
module buffer_storage |  | 2014-12-11: done
module chooser |  | 2014-12-12: done
module arbiter_logic |  | 2014-12-12: done
module arbiter |  | 2014-12-12: done
module direction_analyzer |  | 2014-12-12: done
module com_dir_logic |  | 2014-12-12: done
module valid_tester |  | 2014-12-11: done
module output_data_logic |  | 2014-12-12: done
module crossbar_switch |  | 2014-12-12: done
module input_buffer |  | 2014-12-12: done
module router |  | 2014-12-16: done
module network |  | 2014-12-17: done
Subunits with assertions to make self-testing
module chooser | done
module com_dir_logic | done
module header_body_logic |  | 2014-12-11: done
module header_body_record |  | 2014-12-11: done
Subunits with their testbench to test correctness
module output_data_logic |  | 2014-12-10: done
module arbiter |  | 2014-12-11: done
module direction_analyzer |  | 2014-12-11: done
module buffer_storage |  | 2014-12-04: BUG; 2014-12-11: done
Feature 1 data storage
send one data flit to a router, it can be received and stored |  | 2014-12-15: done
send invalid data flit to a router, it will not be stored |  | 2014-12-15: done
send one data flit to a router, it will be sent out unchanged by that router later |  | 2014-12-15: done
send data flits to random routers on the network |  | 2014-12-15: done
Feature 2 count numbers
after reset credit counter is set five |  | 2014-12-15: done
set up_i high |  | 2014-12-15: done
set down_i high |  | 2014-12-15: done
set up_i high for five clock cycles |  | 2014-12-15: done
set down_i high for five clock cycles |  | 2014-12-15: done
set up_i and down_i high simultaneously |  | 2014-12-15: done
set up_i high when counter value is five |  | 2014-12-15: done
set down_i high when counter value is zero |  | 2014-12-15: done
Feature 3 data transfer
send one data flit to a router, it can be sent out in right direction |  | 2014-12-17: done
send another four data flit to the same router, it can be sent out in the previous direction |  | 2014-12-17: done
send one more data flit to the same router, it will be sent out in its own right direction |  | 2014-12-17: done
send flits continuously to a router with the same desired output |  | 2014-12-17: done
send flits continuously to a router with different desired output |  | 2014-12-17: done
send two flits simultaneously to one router with different desired output |  | 2014-12-17: done
send five flits to one router with different desired output |  | 2014-12-17: done
send one flit to random routers on the network |  | 2014-12-17: done
randomly send flits to any possible routers |  | 2014-12-17: done
Feature 4 arbitration
arbitration functions for two data flits |  | 2014-12-15: done
arbitration funcitons for two sequences of flits |  | 2014-12-15: done
arbitration functions for two sequences of flits with fairness |  | 2014-12-15: done
arbitration functions for four data flits |  | 2014-12-15: done
arbitration functions with fairness for at most four flits simultaneously |  | 2014-12-15: done
arbitration functions for four sequences of flits with fairness |  | 2014-12-15: done
arbitraion always happen with crowded flits to a router |  | 2014-12-15: done
Logic test
send one flits continuously to a router |  | 2014-12-16: done
send five flits continuously to a router with different desired output direction |  | 2014-12-16: done
send five sequences of flits continuously to a router with different desired output direction |  | 2014-12-16: done
send four sequences of flits continuously to a router with the same desired output direction |  | 2014-12-16: done
send five flits simultaneously to random routers |  | 2014-12-16: done
send four sequences of flits simultaneously to random routers |  | 2014-12-16: done
Reset tests
Dynamic reset (middle of simulation) |  | 2014-12-17: done
Corner cases
long critical path with all passing input buffers full |  | 2014-12-16: done
one router continuously send out data flits |  | 2014-12-16: done
input buffers become full |  | 2014-12-16: done
input flits still come when the local input buffer is full |  | 2014-12-16: done
credit counter becomes empty |  | 2014-12-16: done
high reset density |  | 2014-12-16: done
high density of flits on the network |  | 2014-12-16: done
Final random testing and coverage assessment
Randomize the testbench parameters |  | 2014-12-17: done
Run at least 1 million cycles of random simulation |  | 2014-12-17: done
assess the structural coverage |  | 2014-12-17: done
assess the functional coverage |  | 2014-12-17: done
Error tolerance test
wrong desired output
same input and desired output
multiple desired output for one flit
one bit abnormal change randomly during the flit transfer
Performance validation
send one flit to an empty router
send flits continuously to a router
send five flits simultaneously a router
send five flits simultaneously to random routers
Exception event hit rate
Performance gains
Overall bandwidth
Overall latency